## PRODUCT BACKLOG
Monopoly Game
PRODUCT BACKLOG
User Story ID | User Story | Estimate (size) | Priority | Sprint
US005 | The Game Board consists of a sequence of Game Board elements and space for the Community Chest and Chance Card decks. | Large | 1 | 1
US006 | A Game Board element is a GO space, Property spaces, Community Chest space, Chance space, Jail space, Railroad spaces, Free Parking space, Electric Company space, Water Works space, Luxury Tax space, Income Tax space, and Goto Jail space | Medium | 1 | 1
US007 | A Game Board element has a collections of Tokens that currently occupy that element and a sequence of actions that occur for Players who land on each element. | Small | 1 | 1
US009 | Movement of Player Tokens is controlled by the roll of 2 six-sided die. A Player's token is moved the number of Board Spaces indicated by the sum of the two die. If a player roll doubles then they can move again. If a Player rolls doubles 3 times in a row then they goto Jail | Small | 1 | 1
US013 | Chance Cards is a deck of cards that contain actions that will occur when a card is drawn from the deck | Medium | 1 | 1
US014 | Community Chest Cards is a deck of cards that contain actions that will occur when a card is drawn from the deck | Medium | 1 | 1
US008
US012 | A Player has a Token that they select, board position of their token, Money, a collection of owned properties, and a collection of Mortgaged properties. Players must have a means to accomplish each step of a turn. Player's can mortgage properties even when it is not their turn. Player's must be able to determine the monoplies that they own. They must be able to buy houses and hotel for Properties that belong to a monopoly. The houses and hotels must be evenly distributed among the Properties in a monopoly. Players have an a sequence of steps that they must follow to complete their turn. These steps must be able to change dynamically depending on the Board Space they land on. | Large | 1 | 2
US015 | Player Tokens are a set of objects including Top hat, Thimble, Iron, Boot, Battleship, Cannon, Race car, Scottie dog, Wheelbarrow. Tokens have an owner which is a Player. Each Token should have an icon that represents the token. | medium | 1 | 2
US001 | Each Game Board space must have an action associated with it that controlls what happens when a Player lands on that board space. The Game Board space a Player lands on will determine the steps in the Players turn. | Large | 1 | 2
US002 | A game must have 2 to 4 Players. | Small | 3 | 2
US003 | The Banker is not a Player, it a separate entity that is simulated by the program. The Banker has an infinite amount of money, must be able to collect rent, must have a collection of Title Deeds for each Property, must be able to sell Properties to a Player, must be able to auction a Property, must be able to mortgage properties, must be able to pay $200 to Players that land on or pass the Go Board space, must be able to receive money from Players as directed by Community Chest, Chance cards, Luxury Tax, and other payments Players may have to make. Must maintain a collection of 32 Houses and 32 Hotels and have the ability to sell and buy Houses and Hotels. Banker cannot sell a House or Hotel if all 32 of them have already been sold. | Large | 1 | 2
US001 | The winner will be the wealthiest player through buying, renting and selling property. If all Players agree to end game, the winner is the wealthiest Player. If all but one player has gone bankrupt then that Player is the winner | Small | 4
US004 | One of the 2 to 4 players must be a Player simulated by the computer | Large | 4
US010 | The Game State should provide an interface to the Controller and the View so that they can modify the Game State and get the current status of the Game State.
US016 | Property Title Deed Cards is a deck of cards that contain all information regrading a property, such as, Color, Name, Basic Rent, Number of Houses, Number of Hotels, Rent with 0 – 4 houses, Rent with Hotel, Mortgage Value, House purchase cost, Hotel purchase cost, whether or not the Property is mortgaged, and the cost to un-mortgage the property. | Medium | 1 | 2
US017 | Implement Houses. A House should have an icon that represents it. | Small | 1
US018 | Implement Hotels. A Hotel should have an icon that represents it. | Small | 1
US011 | Implement a Player's turn. Each step in a Player's turn should be implemented independently of all other steps. | Medium | 1 | 2
US020 | The Game State has a Game Board, collection of 2 - 4 Players, Dice, and a Banker. The Game State initializes a new game by creating a Game Board, creating a Banker, creating all Players (including the somputer simulated Player), allow each Player to choose a Token, and allocating $1,500 from the Bank to each Player. | Large | 1 | 2
US021 | The Computer Controlled Player will simulate the actions of a Human Player. It will make decisions based on Random Numbers and set percentages. It will have several strategies depending on its current state that can be changed dynamically. | Large | 3
US022 | The GUI will display the current state of the game and allow Players to perform actions that they are allowed. It should indicate the Player whose turn it is and provide buttons (or other GUI components) that guild each player through the sequence of actions allowed for their turn. | Large | 5
US023 | The Controller is a set of classes that implement the listeners for the components displayed by the GUI. | Large | 5
US024
US025
US026
US027
US028
US029
US030
US031
US032
US033
US034
US035
US036
US037
US038
US039
US040
US041
US042
US043
US044
US045
US046
US047
US048
US049
US050
US051
US052
US053
US054
US055
US056
US057
US058
US059
US060
US061
US062
US063
US064
US065
US066
US067
US068
US069
US070
US071
US072
US073
US074
US075

## PROJECT DETAILS
PROJECT NUMBER | 1
PROJECT NAME | Monopoly Game
PROJECT MANAGER | Greg Schaper
DATE | 2025-02-17
VERSION | 1

## DROPDOWN MENUS
PRIORITY | SPRINT
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6
7
8
9
10
TO EDIT THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Source to match the values you want to appear in the menu.
TO DELETE THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Allow to Any value.

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel